Table of Contents

# Rollback and Contingency Plan — DentalCare Pro Migration

| Field | Value |
| --- | --- |
| Document ID | MIG-RBK-001 |
| Version | 1.4 |
| Effective Date | 2025-08-15 |
| Review Date | 2026-02-15 |
| Owner | James Ortiz — IT Operations Manager |
| Classification | Internal — Confidential |

## Version History

| Version | Date | Author | Changes |
| --- | --- | --- | --- |
| 1.0 | 2024-06-01 | James Ortiz | Initial rollback plan |
| 1.1 | 2024-10-15 | David Park | Added service-level rollback procedures |
| 1.2 | 2025-02-01 | James Ortiz | Phase 1 rollback testing results |
| 1.3 | 2025-05-15 | James Ortiz | Blue/green deployment rollback automation |
| 1.4 | 2025-08-15 | James Ortiz | Updated with Phase 1 lessons learned |

## 1. Purpose

This document defines the rollback and contingency procedures for the DentalCare Classic → DentalCare Pro migration. It ensures that any failed migration phase can be reversed within the defined Recovery Time Objective (RTO) without data loss, ensuring continued patient care and business operations.

## 2. Rollback Triggers

### 2.1 Automatic Rollback Triggers

The following conditions automatically trigger a rollback:

| Trigger | Detection Method | Rollback Type |
| --- | --- | --- |
| API error rate > 15% for 5+ minutes | CloudWatch Alarm | Application (blue/green) |
| Health check failures on > 50% of tasks | ALB health check | Application (blue/green) |
| Database connection failures > 100/minute | Application metrics | Application (blue/green) |
| Data validation failure > 1% records | Migration validation suite | Full database rollback |
| Financial balance mismatch > $1.00 total | Reconciliation report | Full database rollback |

### 2.2 Manual Rollback Triggers

The Incident Commander (James Ortiz or backup) may decide to trigger a manual rollback for:

| Scenario | Decision Maker |
| --- | --- |
| Critical user-reported functionality gap | Incident Commander |
| Unacceptable performance degradation | Incident Commander |
| Compliance concern (audit trail gap, PHI exposure) | Compliance Officer |
| Stakeholder loss of confidence | Practice Director |
| Partial data migration (some records missing) | Data Migration Lead |
| External system integration failure (insurance, lab) | Integration Lead |

## 3. Rollback Procedures by Type

### 3.1 Application-Level Rollback (Blue/Green Deployment)

Estimated Duration: 5-10 minutes Data Impact: None (database unchanged) When: New application version has issues but data migration is intact

| Step | Action | Responsible | Duration |
| --- | --- | --- | --- |
| 1 | Decision to rollback communicated | Incident Commander | 1 min |
| 2 | ALB target group switched from green to blue | DevOps Engineer | 2 min |
| 3 | Health checks verified on blue (old version) | DevOps Engineer | 2 min |
| 4 | Green (new version) ECS tasks stopped | DevOps Engineer | 1 min |
| 5 | DNS cache flush confirmed (CloudFront invalidation) | DevOps Engineer | 3 min |
| 6 | Smoke tests on blue environment | QA Engineer | 5 min |
| 7 | User notification: “Service restored” | Communications | 2 min |
| 8 | Post-rollback monitoring (enhanced, 2 hours) | DevOps Engineer | Ongoing |

Terraform Command:

terraform apply -var="active_target_group=blue" -auto-approve

### 3.2 Database Rollback (Full Migration Reversal)

Estimated Duration: 45-90 minutes Data Impact: Data written to new system during parallel run must be reconciled When: Data migration validation fails, or fundamental schema issues discovered

| Step | Action | Responsible | Duration |
| --- | --- | --- | --- |
| 1 | Decision to rollback communicated | Incident Commander | 1 min |
| 2 | Spring Boot application stopped (all services) | DevOps Engineer | 2 min |
| 3 | Any transactions since cutover exported from new DB | DBA | 15 min |
| 4 | Legacy VB6 database restored from pre-migration backup | DBA | 30 min |
| 5 | Post-cutover transactions replayed to legacy DB | DBA + Dev | 15 min |
| 6 | Legacy VB6 application re-enabled (read-write) | IT Operations | 5 min |
| 7 | Legacy VB6 smoke tests | QA Engineer | 10 min |
| 8 | User notification: “Legacy system restored” | Communications | 2 min |
| 9 | Post-rollback data reconciliation | Data Team | 4 hours |
| 10 | Root cause analysis initiated | Dev Team | Next day |

### 3.3 Service-Level Rollback (Single Microservice)

Estimated Duration: 5-15 minutes Data Impact: Minimal — only affects specific service When: Individual service issues while others remain functional

| Step | Action | Responsible | Duration |
| --- | --- | --- | --- |
| 1 | Identify failing service from monitoring | DevOps Engineer | 2 min |
| 2 | Route traffic for affected service to legacy facade | DevOps Engineer | 3 min |
| 3 | Roll back ECS service to previous task definition | DevOps Engineer | 5 min |
| 4 | Or: activate legacy VB6 module for affected function | IT Operations | 5 min |
| 5 | Verify service health | QA Engineer | 5 min |
| 6 | Monitor for ripple effects on dependent services | DevOps Engineer | 15 min |

## 4. Contingency Plans

### 4.1 Contingency: Complete Migration Failure

If the migration cannot proceed and rollback to legacy is required long-term:

| Action | Timeline | Responsible |
| --- | --- | --- |
| Full rollback to legacy VB6 system | Immediate | IT Operations |
| All-hands post-mortem meeting | Within 48 hours | Project Leadership |
| Root cause analysis with remediation plan | Within 1 week | Dev + Architecture |
| Stakeholder communication (clinics, patients) | Within 24 hours | Communications |
| Updated migration timeline | Within 2 weeks | Project Manager |
| Re-test in staging before next attempt | 2-4 weeks | QA Team |

### 4.2 Contingency: Partial Migration (Stuck Between Systems)

If some clinics are on the new system and others remain on legacy:

| Action | Timeline | Responsible |
| --- | --- | --- |
| Identify which clinics are on which system | Immediate | IT Operations |
| Establish data synchronization between systems | Within 4 hours | Dev Team |
| Communication to each clinic about their status | Within 2 hours | Office Managers |
| Prioritized migration/rollback per clinic | Within 24 hours | Project Leadership |
| Daily sync validation between systems | Until resolved | Data Team |

### 4.3 Contingency: Cloud Provider Outage

If AWS experiences a regional outage during migration:

| Action | Timeline | Responsible |
| --- | --- | --- |
| Pause migration immediately | Immediate | Incident Commander |
| Activate legacy VB6 system (on-premises) | Within 30 min | IT Operations |
| Monitor AWS status page | Continuous | DevOps Engineer |
| If outage > 4 hours: full rollback to legacy | 4 hours | Incident Commander |
| If outage < 4 hours: resume migration | After restoration | Data Migration Lead |
| DR failover to us-west-2 if available | Within 1 hour | DevOps Engineer |

### 4.4 Contingency: Data Corruption During Migration

| Action | Timeline | Responsible |
| --- | --- | --- |
| Immediately halt migration ETL pipeline | Immediate | Data Migration Lead |
| Identify scope of corruption (which tables/records) | Within 1 hour | DBA + Dev Team |
| If < 5% of records affected: selective re-migration | Within 4 hours | Data Team |
| If > 5% of records affected: full rollback | Within 2 hours | Incident Commander |
| Forensic analysis of corruption cause | Within 24 hours | Dev Team |
| Re-validate ETL pipeline with additional checks | Before retry | QA Team |

## 5. Communication Plan During Rollback

### 5.1 Internal Communication

| Audience | Method | Template | Timing |
| --- | --- | --- | --- |
| IT Team | Slack #incident channel | Technical status updates | Real-time |
| Clinical Staff | Email + phone tree | “System status update” | Every 30 minutes |
| Front Desk Staff | In-app banner + email | “System availability notice” | Every 30 minutes |
| Management | Email + phone | “Migration status briefing” | Every hour |
| Executive Leadership | Phone call | “Executive situation report” | On trigger + hourly |

### 5.2 External Communication

| Audience | Method | Template | Timing |
| --- | --- | --- | --- |
| Patients with appts | SMS (if opted in) | “Appointment confirmation” | If impact > 2 hrs |
| Insurance partners | Email to EDI contacts | “System maintenance notice” | Pre-scheduled |
| Lab partners | Email | “System maintenance notice” | Pre-scheduled |

## 6. Rollback Testing Schedule

| Test | Frequency | Last Test | Next Test | Result |
| --- | --- | --- | --- | --- |
| Blue/green deployment rollback | Monthly | 2025-07-15 | 2025-08-15 | Pass |
| Database backup restoration | Monthly | 2025-07-15 | 2025-08-15 | Pass |
| Full migration rollback (staging) | Quarterly | 2025-06-01 | 2025-09-01 | Pass |
| Service-level rollback | Monthly | 2025-07-15 | 2025-08-15 | Pass |
| Communication plan test | Quarterly | 2025-04-01 | 2025-07-01 | Pass |
| DR failover test | Semi-annually | 2025-03-15 | 2025-09-15 | Pass |

## 7. Post-Rollback Procedures

### 7.1 Immediate (0-4 hours)

- Verify legacy system is fully operational

- Verify all clinic locations can access the system

- Verify patient data integrity (spot checks)

- Verify appointment schedule is intact

- Verify billing/claims processing is functional

- Monitor for any residual issues

### 7.2 Short-Term (4-48 hours)

- Complete data reconciliation between systems

- Document all issues discovered during migration

- Conduct initial root cause analysis

- Brief all stakeholders on status and next steps

- Update migration timeline if needed

### 7.3 Medium-Term (1-4 weeks)

- Formal post-mortem meeting with all teams

- Root cause analysis report completed

- Remediation plan developed and approved

- Re-testing in staging environment

- Updated risk assessment

- Go/no-go decision for next migration attempt

## 8. Emergency Contacts

| Role | Primary | Phone | Backup | Phone |
| --- | --- | --- | --- | --- |
| Incident Commander | James Ortiz | (555) 234-5681 | David Park | (555) 234-5690 |
| DBA / Database | Kevin Rodriguez | (555) 234-5685 | James Ortiz | (555) 234-5681 |
| DevOps Engineer | Lisa Thompson | (555) 234-5686 | Kevin Rodriguez | (555) 234-5685 |
| Security Officer | Michael Chen | (555) 234-5678 | James Ortiz | (555) 234-5681 |
| Compliance Officer | Dr. Sarah Kim | (555) 234-5679 | Patricia Gomez | (555) 234-5680 |
| Practice Director | Dr. Alan Brooks | (555) 234-5683 | Dr. Lisa Wong | (555) 234-5688 |
| AWS Support | Enterprise Support | (888) 555-0100 | — | — |
| Communications Lead | Angela Martinez | (555) 234-5682 | Dr. Alan Brooks | (555) 234-5683 |

## 9. Approval

| Role | Name | Date |
| --- | --- | --- |
| IT Operations Manager | James Ortiz | 2025-08-15 |
| Lead Architect | David Park | 2025-08-15 |
| Practice Director | Dr. Alan Brooks | 2025-08-15 |

This document is reviewed quarterly. Next review: 2026-02-15. Contact: ops@dentalcarepro.com